## Assignment Usage withEV
Tasks | All
Data
Year | Quarter | Week | Resources | Earned Value | Planned Value | AC | Actual Cost | Budget Cost | Baseline Budget Work | Actual Work | Baseline Budget Cost | Baseline Work | Baseline Cost | Budget Work
2022 | Q4 | Week 40 | Nguy?n Hoàng Minh | 277.7143 | 288 | 288 | 288 | 0 | 0 | 24 | 0 | 24 | 288 | 0
|  |  | Ph?m Thái Ngân | 256 | 256 | 256 | 256 | 0 | 0 | 32 | 0 | 32 | 256 | 0
|  | Week 41 | Nguy?n Hoàng Minh | 370.2857 | 768 | 384 | 96 | 0 | 0 | 8 | 0 | 40 | 480 | 0
|  |  | Ph?m Thái Ngân | 320 | 576 | 320 | 64 | 0 | 0 | 8 | 0 | 40 | 320 | 0
|  | Week 42 | Nguy?n Hoàng Minh | 370.2857 | 864 | 384 | 0 | 0 | 0 | 0 | 0 | 8 | 96 | 0
|  |  | Ph?m Thái Ngân | 320 | 640 | 320 | 0 | 0 | 0 | 0 | 0 | 8 | 64 | 0
| Q4 Total |  |  | 690.2857 | 1504 | 704 | 704 | 0 | 0 | 72 | 0 | 152 | 1504 | 0
2022 Total |  |  |  | 690.2857 | 1504 | 704 | 704 | 0 | 0 | 72 | 0 | 152 | 1504 | 0
Grand Total |  |  |  | 690.2857 | 1504 | 704 | 704 | 0 | 0 | 72 | 0 | 152 | 1504 | 0